## Functionality
S	D	SS	Section	Details	Sub-Details	Player	Message Input	Message Output	Function Points	Dev Status	Test Status	Comment
00			General						4	100%	0%
00	01			Settings
00	01				Dark Mode Enable/Disable				High	1.0
00	02			About
00	02				About Text				High	1.0
00	03			Home
00	03				Home Screen				High	1.0		Display Name does show up when first updated.
00	04			Style
00	04				Develop Style				High	1.0		Simple to start, Improve in Rel 2
00	05			Updates
00	05				Community Count Refresh				Med
01			User						4	100%	0%
01	01			Register Player					High	1.0
01	02			Update Profile					High	1.0
01	03			Unregister Player					Med
01	04			Sign In					High	1.0
01	05			Sign Out					High	1.0
02			Community						3	100%	0%
02	01			Add Community		Owner			High	1.0
02	02			Edit Community		Owner			High	1.0
02	03			Delete Community		Owner			Med	1.0
03			Members						3	100%	100%
03	01			Add Member		Owner		20010	Med	1.0	Yes
03	02			Update Member (Credits)		Owner		20020	Med	1.0	Yes
03	03			Remove Member		Owner		20030	High	1.0	Yes
04			Series						3	100%	0%
04	01			Add Series					High	1.0
04	02			Edit Series					High	1.0
04	03			Delete Series					High	1.0
05			Access						2	100%	0%
05	01			Add Community Access to Series					High	1.0
05	03			Delete Community Access from Series					Med	1.0
06			Games						5	100%	0%
06	01			Add Game					High	1.0
06	02			Edit Game					High	1.0
06	03			Delete Game					Med	1.0
06	04			View Games (Series→Games)					High	1.0
06	05			View Games (Membership→Games)					High	1.0
06	06			Assign Square (Owner)				20005	High	1.0
06	07			Request Square (Player)				00003	High	1.0
06	08
06	09
07			Memberships						3	100%	67%
07	01			Add to Community Request		Player		00010	High	1.0	Yes
07	02			Update Membership Credits Request		Player		00020	High	1.0
07	03			Remove from Community Request		Player		00030	High	1.0	Yes
08			Boards						8	88%	0%
08	01			View Board					High	1.0
08	02			Set Scores for Columns and Rows					High	1.0
08	03			Assign Square (Owner)				20005	High	1.0
08	04			Request Square (Player)				00003	High	1.0
08	05			Set Results by Quarter					High	1.0
08	06			Set Splits by Quarter					High	1.0		Can change splits after, maybe disable once scores locked.
08	07			Fill Remaining Squares					High	1.0
08	08			Distribute Credits					High	0.0
09			Messages						28	100%	29%
09	01			Acknowledge Community Membership Add		Player	20010	30010		1.0	Yes	03.01
09	02			Acknowledge Community Membership Update Notification		Player	20020	30020		1.0	Yes	03.02
09	03			Acknowledge Community Membership Remove Notification		Player	20030	30030		1.0	Yes	03.03
09	04			Community Membership Add Response (Accept)		Owner	00010	10010		1.0	Yes	07.01
09	05			Acknowledge Community Membership Add (Accepted)		Player	10010	30010		1.0	Yes	09.04
09	06			Community Membership Add Response (Reject)		Owner	00010	10011		1.0	Yes	07.01
09	07			Acknowledge Community Membership Add (Rejected)		Player	10011	30011		1.0	Yes	09.06
09	08			Community Membership Update Response (Accept)		Owner	00020	10020		1.0		07.02
09	09			Acknowledge Community Membership Update (Accepted)		Player	10020	30020		1.0		09.08
09	10			Community Membership Update Response (Reject)		Owner	00020	10021		1.0		07.02
09	11			Acknowledge Community Membership Update (Rejected)		Player	10021	30021		1.0		09.10
09	12			Community Membership Remove Response (Accept)		Owner	00030	10030		1.0	Yes	07.03
09	13			Acknowledge Community Membership Remove (Accepted)		Player	10030	30030		1.0	Yes	09.12
09	14			Community Membership Remove Response (Reject)		Owner	00030	10031		1.0	Yes	07.03
09	15			Acknowledge Community Membership Remove (Rejected)		Player	10031	30031		1.0	Yes	09.13

09	12			Reject Community Membership Remove Request		Owner	00030	10003		1.0		07.03
09	#REF!			Acknowledge Community Membership Remove Response (A/R)		Player	10003	30005		1.0
09	11			Community Membership Remove Response (Accept)		Owner	00030	10003		1.0		07.03
09	13			Accept Community Membership Remove Response		Player				1.0		09.04, 09.05
09	14			Accept Member Edit (Credits) Notification		Player				1.0		03.03
09	15			Accept Membership Add Credits Notification				20004		1.0		07.03
09	16			Reject Membership Add Credits Notification				20004		1.0		07.03
09	17			Accept Membership Add Credit Notification						1.0		09.08, 09.09
09	18			Accept Membership Remove Credits Request				20004		1.0		07.04
09	19			Reject Membership Remove Credits Request				20004		1.0		07.04
09	20			Accept Membership Remove Credit Notification						1.0		09.08, 09.09
09	21			Accept Square Assignment Notification						1.0		08.03
09	22			Accept Square Request				20006		1.0		08.04
09	23			Reject Square Request				20006		1.0		08.04
09	24			Accept Square Request Response						1.0		09.15, 09.16
09	#REF!			Acknowledge Community Membership Update Response (A/R)		Player	10002	30011		1.0
09	#REF!			Acknowledge Community Membership Add (Accepted)		Player	10020	30020		1.0		09.01
				Acknowledge Community Membership Add (Rejected)		Player	10021	30021		1.0		09.01

## Enhanements
EnhNo	S	Section	Prio	Dev Status	Comment
001	08	Messages	Low	0	Clean up the messages page to eliminate users without messages and make the messages cleaner. Maybe a two step process … pick users => view messages.
002	02	User	Med	0	Ensure Players are validated before any transactions.

## Defects
DefNo	S	Section	Prio	Dev Status	Comment
1	8	Messages	Low	0