## Functionality
S	D	SS	Section	Details	Sub-Details	Player	Message Output	Function Points	Dev Status	Test Status	Comment
00			General					4	100%	100%
00	01			Settings
00	01				Dark Mode Enable/Disable			High	1.0	Yes
00	02			About
00	02				About Text			High	1.0	Yes
00	03			Home
00	03				Home Screen			High	1.0	Yes	Display Name does show up when first updated.
00	04			Style
00	04				Develop Style			High	1.0	Yes	Simple to start, Improve in Rel 2
00	05			Updates
00	05				Community Count Refresh			Med
01			User					4	100%	100%
01	01			Register Player				High	1.0	Yes
01	02			Update Profile				High	1.0	Yes
01	03			Unregister Player				Med
01	04			Sign In				High	1.0	Yes
01	05			Sign Out				High	1.0	Yes
02			Community					3	100%	100%
02	01			Add Community		Owner		High	1.0	Yes
02	02			Edit Community		Owner		High	1.0	Yes
02	03			Delete Community		Owner		Med	1.0	Yes
03			Members					3	100%	100%
03	01			Add Member		Owner	20001	Med	1.0	Yes
03	02			Edit Member (Credits)		Owner	20002	Med	1.0	Yes
03	03			Remove Member		Owner	20003	High	1.0	Yes
04			Series					3	100%	100%
04	01			Add Series				High	1.0	Yes
04	02			Edit Series				High	1.0	Yes
04	03			Delete Series				High	1.0	Yes
05			Access					2	100%	100%
05	01			Add Community Access to Series				High	1.0	Yes
05	03			Delete Community Access from Series				Med	1.0	Yes
06			Games					5	100%	100%
06	01			Add Game				High	1.0	Yes
06	02			Edit Game				High	1.0	Yes
06	03			Delete Game				Med	1.0	Yes
06	04			View Games (Series→Games)				High	1.0	Yes
06	05			View Games (Membership→Games)				High	1.0	Yes
06	06			Assign Square (Owner)			20005	High	1.0	Yes
06	07			Request Square (Player)			00003	High	1.0	Yes
06	08
06	09
07			Memberships					5	100%	100%
07	01			Add to Community Request		Player	00001	High	1.0	Yes
07	02			Remove from Community Request		Player	00002	High	1.0	Yes
07	03			Membership Add Credits Request		Player	00004	High	1.0	Yes
07	04			Membership Remove Credits Request		Player	00004	High	1.0	Yes
07	05			Delete Membership		Player		High	1.0	Yes
08			Boards					8	88%	88%
08	01			View Board				High	1.0	Yes
08	02			Set Scores for Columns and Rows				High	1.0	Yes
08	03			Assign Square (Owner)			20005	High	1.0	Yes
08	04			Request Square (Player)			00003	High	1.0	Yes
08	05			Set Results by Quarter				High	1.0	Yes
08	06			Set Splits by Quarter				High	1.0	Yes	Can change splits after, maybe disable once scores locked.
08	07			Fill Remaining Squares				High	1.0	Yes
08	08			Distribute Credits				High	0.0
09			Messages					17	100%	100%
09	01			Accept Community Membership Add Request		Owner	10001		1.0	Yes	07.01
09	02			Reject Community Membership Add Request		Owner	10001		1.0	Yes	07.01
09	03			Accept Community Membership Add Response		Player			1.0	Yes	09.01, 09.02
09	04			Accept Community Membership Remove Request		Owner	10002		1.0	Yes	07.02
09	05			Reject Community Membership Remove Request		Owner	10002		1.0	Yes	07.02
09	06			Accept Community Membership Remove Response		Player			1.0	Yes	09.04, 09.05
09	07			Accept Member Edit (Credits) Notification		Player			1.0	Yes	03.03
09	08			Accept Membership Add Credits Notification			20004		1.0	Yes	07.03
09	09			Reject Membership Add Credits Notification			20004		1.0	Yes	07.03
09	10			Accept Membership Add Credit Notification					1.0	Yes	09.08, 09.09
09	11			Accept Membership Remove Credits Request			20004		1.0	Yes	07.04
09	12			Reject Membership Remove Credits Request			20004		1.0	Yes	07.04
09	13			Accept Membership Remove Credit Notification					1.0	Yes	09.08, 09.09
09	14			Accept Square Assignment Notification					1.0	Yes	08.03
09	15			Accept Square Request			20006		1.0	Yes	08.04
09	16			Reject Square Request			20006		1.0	Yes	08.04
09	17			Accept Square Request Response					1.0	Yes	09.15, 09.16

## Enhanements
EnhNo	S	Section	Prio	Dev Status	Comment
001	08	Messages	Low	0	Clean up the messages page to eliminate users without messages and make the messages cleaner. Maybe a two step process … pick users => view messages.
002	02	User	Med	0	Ensure Players are validated before any transactions.

## Defects
DefNo	S	Section	Prio	Dev Status	Comment
1	8	Messages	Low	0